## Mandatory Placement
DRAFT
1. Implementation Steps for ELI Mandatory Placement
Effective Practice and Coordination | Strategies Related to the Effective Practice | Assignment | Assigned to: | Resources needed: | Timeline & Status Reporting | Next Report | Progress Results
Establish mandatory placement for ESL, English, and mathematics courses. Modify math placement criteria to allow specific placement into modular or special topics basic skills courses. Explore the use of other developmental-level placement tests. (D.7) | Establish pre-requisites for basic skills courses in ESL, English and Math. (D.5.1),(D.7.2) | ESL, Math and English curriculum representatives to establish basic skills as pre-requisites for collegiate level courses. A pre-requisite series will also be developed for ESL to English (dependent on curriculum alignment #4). | Math, English and ESL departments and curriculum representatives | Faculty time, hire more English, ESL and Math faculty | * 8/14/2008 * 10/08 board meeting approval * 9/08 report to ELI coordinators, catalog and scheduling decisions, curriculum committee, increase availability of assessment times, review banner programming and testing Implement by spring 09 | 9/1/2008 9/15/08 10/01/08 10/15/08 11/01/08
| Develop an assessment plan. (A.4.1), (D.7.1) | Validate the cut scores for assessment tests, establish resources and processes for assessment, improve placement in ESL based on CELSA scores, complete research on successful completion of courses pre-mandatory vs. post-mandatory | Tim Garner | Assessment tool, time | *Assessment plan by 09/08 * First set of data by summer 09 | 10/01/08 02/01/09 06/01/09
| Develop marketing strategy and materials. (A.1.4) | Create a marketing plan to high schools and new students to include the off-site ESL and other locales (include P-16 math alignment) and teacher to teacher meetings, refine marketing methods, update catalog and schedule of classes and develop a flow chart in the catalog for basic skills. | Steve Renton, Gail Robinson and deans of student services, Robert Urtecho, Math, English and ESL faculty coordinators | Steve Renton will identify necessary resources through the marketing plan | *First draft of plan by 10/01/08 *Marketing prior to Spring 09 | 10/1/2008 12/ 01/08 2/01/09
| Align curriculum to competency levels, time, resources and SLO's. (D.7.3) | Ensure that basic skills course curriculum is aligned to competency levels. Align the way we test students in the classroom including exit competencies, assessment methodology, valid assessments, aligning competencies and ensuring students have mastered those competencies. | Academic deans, division chairs, SLO committee and curriculum representatives | Faculty time | *Curriculum alignment report 10/15/08 | 2008-10-15

## TLC
DRAFT
2. Implementation Steps for the ELI Faculty and Staff Training Center
Effective Practice and Coordination | Strategies Related to the Effective Practice | Assignment | Assigned to: | Resources needed: | Timeline & Status Reporting | Next Report | Progress Results
Develop a teaching/learning center (physical presence) based on the mission statement that provides foundation for faculty development. (A.6) | Develop a proposal to create a faculty and staff training center. (A.6.1) | Write a proposal for the location of the new training space | Ron Johnson, Eric Mittlestead and Kathie Lewis, ELI coordinators, ELI steering committee, FEC and PACE | Equipment, budget, IT, staffing, furniture, etc. | * Proposal developed by October 2008 * February 09 proposed budget * April 2009 budget approvals *Equipment requests by Fall 2008 * Fall 2009 grand opening | 8/15/2008 9/15/08 10/1/08
Provide training on developmental education for faculty and staff; establish training protocol and accountability methods, including a needs assessment; and develop training plan. (C.3) | Conduct a needs assessment for faculty and staff training on developmental education. (A.6.3) | Identify a consultant to conduct the needs assessment (Marcy Allen Craig) | David Hurst, ELI faculty coordinators, FEC and PACE will originate the recommendation for hiring of the consultant. | Consultant, money, time | *Hire consultant by September 08 *Conduct needs assessment in Fall 2008 *Identify training resources *Develop training plan by Spring 2009 *Begin training in Fall 2009 | 9/15/08 11/01/08 1/15/09 4/01/09 06/01/09
| Develop the faculty and staff training plan based on the needs assessment results including incentives, marketing, training providers and materials, and external resources. (D.8.1) | Create and develop a working training plan for basic skills that includes faculty/staff time, providers, materials and external resources | FEC and Pace, Kathie Lewis, ELI coordinators | Funding, materials, trainer pay, space, computers, equipment, books, software, etc. | *Draft 3 year training plan and timeline based on needs assessment results presented to ELI coordinators Feb 2009 *Budget proposal Feb 09 *Strategic plan for training and development for 3 years and specific implementation plan for year one April 09 *Provide training Fall 09 | 02/15/09 3/01/09 (marketing) 3/15/09 4/15/09 06/01/09 07/15/09 08/15/09
| Establish training protocol, evaluation and accountability methods. (A.4.4.) | Develop guidelines for evaluation and dissemination of training. Develop training materials: presentations, website, workbooks, etc. | FEC and Pace, Kathie Lewis, ELI coordinators, Equity Committee, Tim Garner, SLO coordinators | Time, budget and materials (application). | *Develop guidelines, forms and materials for training as well as evaluation protocols (change in curriculum and pedagogy, assessment based on SLO's, student success and cultural competency) presented to ELI coordinators by Fall 2008. Implement guidelines by Spring 2009. Report to ELI by February 2009. | 9/15/08 11/01/08 1/15/09 4/01/09 06/01/09

## FYE
DRAFT
3. Implementation Steps for ELI to Expand and Partner FYE
and Mandate Learning Communities for all basic skills classes
Effective Practice and Coordination | Strategies Related to the Effective Practice | Assignment | Assigned to: | Resources needed: | Timeline & Status Reporting | Next Report | Progress Results
Expand FYE and partner FYE and ELI. (A.5) | Expand the current number of FYE offerings. Work with divisions to identify interest, participation and potential themes. (A.5.2), (D.3.1) | The FYE program will work closely with the divisions to identify potential offerings for expansion of FYE. | ELI coordinators, FYE staff, FYE learning council, Frances Gusman, Don Mast | FT HD instructor, FT Retention specialist, FT counselor, room allocation for COUN 110 and HD 120 courses, additional counseling time. | The expansion is ongoing. Fall 2008 the FYE is expanding to 12 learning communities. Plan is expand learning communities, seminar classes and HD classes incrementally. | 11/01/08 3/01/09 7/15/09 11/01/09 | Fall 2008
| Finding space for expansion communities and classes. (A.3.1) | Academic Services and Student Services will work together to identify potential classroom space. | Don Mast and Gail Robinson | Rooms and additional math and English faculty | HD and counseling classes have been assigned one room for fall 08. Further research needs to occur to accommodate expansion for Fall 09. | 3/01/09 7/15/09 11/01/09
Utilize FYE program as a primary resource for all basic skills classes to address both academic and social integration for basic skills students. Expand Human Development class offerings. (D.3) | Expand the learning communities and FYE seminar offerings to accommodate basic skills level students. (D.3.5) | The FYE program will work closely with the divisions to identify links to learning communities, HD classes and seminars for basic skills students. | ELI coordinators, FYE staff, FYE learning council, Frances Gusman, Don Mast | FT HD instructor, FT Retention specialist, FT counselor, room allocation for COUN 110 and HD 120 courses, additional counseling time. | In the Fall 2008 expansion, at least 6 learning communities incorporate basic level courses. Spring 09 and Fall 09 will continue to expand the basic skills offerings. | 11/01/08 3/01/09 7/15/09 11/01/09 | Fall 2008
| Counsel and refer students who test into the basic levels to the FYE program. (D.5.2) | Assess all incoming students and properly place into basic skills courses. Counsel and refer students to the FYE program. | Frances Gusman, Ron Johnson, Assessment Office, Counselors, FYE staff. | Mandatory assessment, additional assessment times and staff, additional counseling staff, additional math and English instructors | Currently through counseling and reg-to-go, students are referred to learning communities. By Fall 09 all students will be assessed and those who test into basic levels will be counseled and referred to FYE offerings. | 11/01/08 3/01/09 7/15/09 11/01/09 | Spring 2008
| Design accountability and outcomes measures for the HD and COUN classes. (A.4.4), (B.2.4.), (B.2.5) | Create a method of CQI for the design of HD 120 and Counseling 110 that incorporates feedback from instructional faculty. Design will include outcomes and output (retention, completion, persistence in sequence). Also, incorporate the climate survey (assessment of student engagement), the FYE version of the NSSE or CSSE and student course evaluations. | Tim Garner | Assessment tool and evaluation plan | Assessment plan by 09/08 First set of data by summer 09 | 10/01/08 02/01/09 06/01/09 | Fall 2008
| Integrate the assessment office and career center as key points of contact for FYE and basic skills students. (A.3.4) | Representatives from the assessment office and career center will serve on the FYE council. Both offices will be key linkages for students to the FYE program. | Frances Gusman, Don Mast, Assessment staff, Career center staff. | Additional assessment staff, reorganize staff in the career center. | Assessment and career center offices will develop a 3-year plan for integration of FYE by early fall 08. Plan implemented in spring 09. | 10/15/08 02/15/09 4/15/09 | Fall 2008

## Curriculum
DRAFT
4. Implementation Steps for ELI to Develop and Align Curriculum for Basic Skills
Effective Practice and Coordination | Strategies Related to the Effective Practice | Assignment | Assigned to: | Resources needed: | Timeline & Status Reporting | Next Report | Progress Results
Develop and align curriculum to assist basic skills students in reading, writing and numeracy. (D.7) | Train faculty and deans on curriculum alignment and development for basic skills course sequences as well as from basic skills courses to other disciplines. Development of best practices, lesson plans, assignments and testing materials. (D.7.1) | The ELI faculty coordinators, division chairs, deans and curriculum committee are all trained on curriculum development and alignment. | Bill Scroggins, ELI chair, ELI coordinators, curriculum committee, deans. | Training, time, and space | Deans and ELI coordinators will be trained in summer 08, curriculum committee receives training in Fall. | 10/01/08 1/15/09
| Curriculum alignment: a) competencies in courses within sequences are taught and mastered in previous courses; b) compare competencies needed to succeed in other classes and across disciplines, c) compare success in subsequent course to competencies in previous course d) bridge ESL to English curriculum and to establish pre-requisites in the sequence (Mandatory Placement #1). (D.5.1), (D.7.1), (D.7.3) | Align and develop curriculum within ESL, math and English and across courses. Develop an institutional SLO for basic skills. Appoint an ELI curriculum committee as a sub-committee of the ELI steering committee to include ELI coordinators for those divisions, division chairs, curriculum reps and SLO coordinators. | Math, English and ESL Deans, division chairs and faculty, SLO coordinators, Curriculum committee, program review steering committee. | Training, time, and space | Develop institutional SLO(s) by September 30, 08. All involved will be trained by end of Fall 08. Incorporate into program review by spring 09 (program review steering committee). Changes to course outlines, SLO's and assessment by the end of spring 09. Validation plan in place by October 15, 08. Validation ongoing beginning in Fall 09. | 10/01/08 10/20/08 12/01/08 3/01/09 06/01/09 09/01/09
| Design accountability and outcome measures for curriculum alignment. (A.4.4), (D.7.2) | Design accountability methods to ensure that curriculum is aligned and that this alignment relates to positive results for student learning. | Tim Garner | Time and assessment tool |  | 1/15/09 3/13/09

## Peer to Peer
DRAFT
5. Implementation Plan ELI for Assisted Learning Beyond the Classroom
Effective Practice and Coordination | Strategies Related to the Effective Practice | Assignment | Assigned to: | Resources needed: | Timeline & Status Reporting | Next Report | Progress Results
Develop an assisted learning strategy for the college. Expand the use of a variety of methods of assisted learning beyond the classroom (e.g. peer-to-peer learning assistance methods, one-on-one tutoring, supplemental instruction, small group instruction, computer assisted instruction). (D.10) | Provide a summit training on assisted learning outside the classroom in order to develop an assisted learning strategy for the college. Incorporate Assisted Learning in the next application for Title V grant. (A.6.2), (C.1.2), (C.2.1) | Provide training on assisted learning and develop a common understanding and strategy at the college. Provide support for assisted learning through a Title V grant. | ELI faculty coordinators, Robert Urtecho, math and English division chairs, Kathie Lewis. | Time and money | Develop timeline based on the Title V grant request for proposal. Provide training in the Fall semester. Develop strategy for college by spring semester. | 10/15/08 12/01/08 3/15/09
| Explore and research options for offering all forms of assisted learning. Research how other colleges organize and manage assisted learning (specifically tutorial labs). (A.5.1) | Research best practices from other campuses and current literature to establish a common definition and model of assisted learning beyond the classroom. | Frances Gusman, Jennifer La Serna, David Hurst, ELI coordinators, Kathie Lewis | Time and money | Research literature on supplemental learning and visit other CC campuses excelling in this area over summer and early fall. *Provide executive summary and recommendations by mid-fall 08. | 10/15/08 12/01/08
| Develop non-credit curriculum for supplemental instruction. (D.2.4), (D.5.3) | The ELI coordinators will work with division curriculum reps to develop and initiate curriculum that support the increased supplemental learning methods. | ELI coordinators, curriculum committee, division reps. | Faculty Time | Report preliminary status report to the ELI steering committee by October. Curriculum should be available by Spring 09. | 10/30/08 2/01/09
| Improve and increase staffing for assisted learning across campus and the types of staff delivery. (D.10.4) | Expand options for staffing for assisted learning, specifically in the math lab, writing center, and tutorial center. Develop a pay structure for staff based on training and experience. | Student Services, Math and English ELI coordinators, DRC director, Kathie Lewis, and Math and English Division chairs. | Staff, LD specialist, Tutors, office space, instructional space | Begin exploring options in Fall and submit budget for staffing by end of Fall. Develop job descriptions for each level of staffing by Fall. Develop recruiting and training plan for staffing by Fall. | 1/15/08 03/15/09
| Design accountability and outcomes measures for assisted learning. (A.4.4), (B.2.4), (B.2.5) | Design an accountability method for assisted learning. Consider outcomes and output (retention, completion) and feedback from instructional faculty and students. | Tim Garner | Time, assessment tool | Assessment plan by 03/09 First set of data by summer 09 | 1/15/09 03/15/09