## COS Hanford
COS Project Master Schedule Draft (11-15-06)
[5 empty] | 2006 |  |  |  | 2007 | [6 empty] | 2007 |  |  |  |  | 2008 |  |  |  |  | 2008 | [6 empty] | 2009 |  |  |  |  | 2009 | [6 empty] | 2010 |  |  |  |  | 2010 | [6 empty] | 2011 |  |  |  |  | 2011 | [6 empty] | 2012 |  |  |  |  | 2012
Item | Activity Description | Duration | Start | Finish | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Hanford Vocational Education Building
5 | Project Submitted to DSA |  | 2006-10-01 | 2007-02-01 | bar: 2006 O to 2006 J
6 | Printing and Prep for Bidding |  | 2007-02-01 | 2007-02-15 | bar: 2007 F
7 | Construction Advertisement |  | 2007-02-15 | 2007-03-22 | bar: 2007 F to 2007 M
8 | Bid Opening Date | 1 | 2007-03-22 | 2007-03-22 | bar: 2007 M
9 | COS Board Agenda for Bid Approval |  | 2007-03-27 | 2007-03-27 | bar: 2007 M
10 | COS Board Approves Bid Award |  | 2007-04-09 | 2007-04-09 | bar: 2007 A
11 | City of Hanford Approves Bid Award |  | 2007-04-03 | 2007-04-03 | bar: 2007 A
12 | Construction |  | 2007-05-01 | 2008-05-01 | bar: 2007 M to 2008 A
13 | Group 2 Equipment Installation |  | 2008-05-01 | 2008-07-01 | bar: 2008 M to 2008 J
14 | Move-In |  | 2008-07-01 | 2008-08-01 | bar: 2008 J
15 | Hold Classes in Building |  | 2008-08-11 | 2008-08-11 | bar: 2008 A
Hanford Public Safety/Educational Center
33 | Architecture (Preliminary Plans) |  | 2007-01-01 | 2007-04-01 | bar: 2006 J to 2007 M
34 | Architecture (Working Drawings) |  | 2007-04-01 | 2008-01-01 | bar: 2007 A to 2007 D
35 | DSA |  | 2008-01-01 | 2008-07-01 | bar: 2007 J to 2008 J
36 | COS Board Authorization to go to bid |  | 2008-07-14 | 2008-07-14 | bar: 2008 J
37 | Printing & Prep for Bidding |  | 2008-07-01 | 2008-08-01 | bar: 2008 J
38 | Construction Advertisement |  | 2008-08-01 | 2008-09-04 | bar: 2008 A
39 | Bid Opening Date |  | 2008-09-04 | 2008-09-04 | bar: 2008 S
40 | Low Bid Document Review |  | 2008-09-04 | 2008-09-30 | bar: 2008 S
41 | Board Agenda for Bid Approval |  | 2008-09-30 | 2008-09-30 | bar: 2008 S
42 | COS Board Approves Bid Award |  | 2008-10-13 | 2008-10-13 | bar: 2008 O
43 | Chancellors Office Authorizes Construction |  | 2008-10-01 | 2008-10-13 | bar: 2008 O
44 | Construction |  | 2008-11-01 | 2010-04-01 | bar: 2008 N to 2010 M
45 | Equipment Installation |  | 2010-04-01 | 2010-07-01 | bar: 2010 A to 2010 J
46 | Move-In |  | 2010-07-01 | 2010-08-01 | bar: 2010 J
47 | Hold Classes in Building |  | 2010-08-16 | 2010-08-16 | bar: 2010 A